## Slide 1: COMMUNITY-BASED PROJECT System of System Engineering (SoSE) Development Program Plan
APG Senior Leadership Cohort Program
Steve Aubert, ARL, stephen.a.aubert.civ@mail.mil, 401-278-0320
Liz Miranda, CECOM, liz.s.miranda.civ@mail.mil, 410-861-7027
Val Novikov, JPEO CBD, valentin.novikov.civ@mail.mil, 410-417-3026
William Oberle, ARL, william.f.oberle.civ@mail.mil, 410-278-4362
George Palafox, CERDEC, george.palafox.civ@mail.mil, 410-395-7454

## Slide 2: Project Overview
Vision: Developing proficient SoSEs within the APG Community
Mission: Develop a plan for establishing a SoSE training program at APG
Specific Cohort Goals:
  Develop a plan and gain senior-level approval
  Determine program construct based on stakeholder’s requirements (e.g., length of program, formal and informal training, rotational developmental assignments, sources of funding)
  Define a transition strategy to ensure continued development of SoSE SMEs
SoSE Development Program Plan
<number>

## Slide 3: Key Benefits
Army
Individuals
Organizations
APG
Holistic technical thinkers
Provides broadening engineering experience
Increases current job performance
Development of future SME SoSEs
Enterprise Workforce Development
Enterprise Level Collaboration
Cross-organizational awareness
Core Competencies
Partnerships
Develops
Supports
Enables
SoSE Development Program Plan
<number>

## Slide 4: Three Major Thrusts For the Team
Identify and arrange formal training.
Interact with Team APG organizations to obtain candidates, developmental assignments, and follow on support.
Work with candidates to plan special or informal training, finalize schedules, and develop formal developmental assignment agreement.
<number>

## Slide 5: Service Options & Attributes
Concurrent Tech Co.
  2.5 Days
  $487K (one-time cost)
Old Dominion Univ.
  Short Course
    4 Days
    $25K
  Long Course ($360K)
    8-4 hrs Sessions (4 Courses, 32 hrs ea.)
    8-8 hrs Sessions (1 Capstone, 64 hrs)
    Certificate & 6 Credits
Cal Tech
  5 Days
  $62K + $2K per each additional student
Stevens Institute
  12 Days/Big $
Customized Designed Program Sustainment
Gov Owned Gov Time Investment
Integrated with Army Ed Sys Thoroughness/Depth
Dynamic (re-tailor) Cost
Depth Time Commitment
Proven Established
Cost/Value
Capstone
Semi-Tailored
Publish Technical Report/Journal
Assimilation of info
Developmental Assessment
Certificate/Credits
Cost Depth
Semi-Tailored
Some Flexibility
Certificate
Big Question Mark
Cost?
Depth?
<number>

## Slide 6: Strategic Steps
Meet with Sponsor Mr. Sverapa - Mid October 2012
  Present Options & Recommendations
Engage Stakeholders
Down Select Service Option
Contract Service Delivery
Identify Developmental Assignment Opportunities
  Advanced Development
  Testing and Evaluation
  Laboratories
Assemble Roster of Trainees
Execute Program - March 2013
Implement Program Sustainment Strategy
<number>

## Slide 7: Backup Slides
<number>

## Slide 8: Draft Development Program Plan
Team APG SoSE Candidate Pool
Team APG Organizations
Candidate & Supervisor Identify Desired Developmental Assignment Competencies
Team APG
List of Organizational Developmental Assignment Competencies
Formal Developmental Assignment Agreement
List of competencies to be acquired
Specific activities of assignment
Expectations for candidate and developmental assignment organization
ID Specialized Training Required for Developmental Assignment
Common Formal SoSE Training
Individual SoSE Development Program Plan Schedule
Candidate and Organizations Negotiate Developmental Assignment
Negotiation
Coordination/Scheduling
<number>

## Slide 9: Key Stakeholders
Pool of Candidates
Future Stakeholders
<number>

## Slide 10: Schedule Template
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Formal Training Block I |  |  |  |  |  |  |  | Formal Training Block II |  |  | 
Special Training I |  |  |  | Special Training II |  |  |  | Special Training III |  |  | 
 |  | Developmental Assignment I |  |  |  | Developmental Assignment II |  |  |  |  | 
Assuming a year long program for the formal training
Overall length TBD for each candidate and the specific
developmental assignment(s) required to achieve the
desired specific competencies and special (informal)
training
<number>

## Slide 11: List of Possible Selection Criteria*
Dept of Subject
Cost/Value
Integrated with Army Ed Sys
Certificate/Credits
Tailorability/Dynamic
Sustainability
Credibility
Time Commitment
Developmental Assignments
Publications
*not currently in order of priority
<number>