## Slide 1: APG Senior Leadership Cohort Program 4
Mid – Term Community Based Project Update
Enrichment of the APG Senior Management Association (E-SMA)

## Slide 2: Team members
E-SMA CBP Team:
  Amy Dean, CMA
  Mark DeVita, ATEC
  Peter Emanuel, ECBC
  Cheri Hardin, ARL
  Adam Rawlett, ARL

## Slide 3: Mission
To create a Strategic Plan to formally document SMA and its goals
Our intent is to augment the success of APG Cohort 3’s SMA by crafting a Strategic Plan that affords the Steering Committee with an organizational objective based ‘lines-of-efforts’ to develop annual campaigns that:
    address the dynamic needs of APG’s GS 14/15 members
    includes concerns of the sponsoring Senior Leaders
    facilitates personal and professional growth
    operates within available financial resources
    diversity SMA offerings to attract a wider audience
Setting a precedent for joining and supplementing prior Cohort CBPs.

## Slide 4: Actions to Date
Project Charter approved, 30 Aug 2012
Initiated a SMA sponsored CBRN Networking event announced via SMA portal, to be conducted 16 Oct @ Edgewood’s CDTF
Effected on-going liaison with SMA Steering Committee, via weekly telecom
Assisted with the set-up/conduct of (and attended) the August SMA Luncheon
Researching organizational Strategic Planning
  Types, formats, organization processes and structures

## Slide 5: Actions Planned
Create Strategic Plan and socialize with current SMA Steering Committee members, challenges to address:
  SMA sustainability, marketing, governance, organizational structure
Conduct CBRN Networking After Action Review and document lessons learned to Steering Committee & SES sponsor
Potentially host another “focused” SMA event / activity
Continue on-going weekly liaison with Steering Committee, via telecom
Assist and attend future SMA Luncheons and Events