## Slide 1
Presentation of COHORT Track B Community Project to GO/SES Panel
26 September, 2012
Sean Buck
William Newton
Abel Salgado
Thomas Mulkern
Bruce Testa

## Slide 2
Vision: A valued and enduring orientation program that articulates APG’s Mission Areas.
Mission: Develop a program that provides employees with an overview on mission area activities at APG and how they support the DoD Acquisition process.
Execute a “pilot run” to demonstrate concept

## Slide 3: AMMO Program Concept
Develop a program to augment the existing new employee orientation
  Introduce new employees to resident activities at APG using the acquisition process as a guide.
  Provide overview presentations, facility tours & information packets.
Project Goals
Complete an orientation program plan
Develop an APG smartbook of organizations and their leadership
Execute at least one pilot run
Develop a transition/sustainment plan

## Slide 4: Project Scope
Pilot participation will leverage the APG Cohort
32 participants for pilot run
Maximum 3-day program
Feedback from participants and organizations
Project Challenges
Gaining support of resident activities
Sustainability & Ownership of program
Funding

## Slide 5: Project Timeline
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Final Report
Tours Identified Org. Commitments
Pilot run
Information Packets Complete
Charter Signed /Project Approved
“Internal” Org Support
RDECOM
CERDEC
ATEC
CECOM
“Other” Tenant Org Support
Briefing to SES/GO Panel
Pilot run individuals Identified

## Slide 6: Backup

## Slide 7: Example of using Acquisition process
Material
Solution Analysis
Technology
Development
Engineering &
Manufacturing
Development
Material
Solution Analysis
Operations &
Support
A
B
C
S&T R&D Testing Fielding Sustainment
Army Research Lab
CERDEC
PEO C3T, PEO IEWS, PMS
ATEC
CECOM
Notes: <number>

## Slide 8: Proposed Schedule
APG Military Mission Orientation Brief Schedule of Events |  |  |  |  |  | 
 | Day 1 | Time (hrs) | Day 2 | Time (hrs) | Day 3 | Time (hrs)
0730 | Introduction | 2 | Program Executive Office Command Control Communications-Tactical (PEO C3T) and Program Executive Office Intelligence Electronic Warfare and Sensors (PEO IEW&S) | 2 | Army Test and Evaluation Command (ATEC), Aberdeen Test Center (ATC), and Army Evaluation Center (AEC) | 2
0800 |  |  |  |  |  | 
0830 |  |  |  |  |  | 
0900 |  |  |  |  |  | 
0930 |  |  |  |  |  | 
1000 | TRAVEL (to ARL) | 0.5 | TRAVEL (to Edgewood) | 0.5 | TRAVEL (to 6001) | 0.5
1030 | Army Research Lab (ARL) Rodman Building | 2 | Edgewood-Chemical Biological Center (ECBC); Tour Public Health Command | 2 | Communications-Electronics Command (CECOM) | 2
1100 |  |  |  |  |  | 
1130 |  |  |  |  |  | 
1200 |  |  |  |  |  | 
1230 | TRAVEL (to Rec Center) | 0.5 | TRAVEL (to Southside Grill) | 0.5 | TRAVEL (to Rec Center) | 0.5
1300 | Lunch | 1 | Lunch | 1 | Lunch | 1
1330 |  |  |  |  |  | 
1400 | TRAVEL (6002) | 0.5 | TRAVEL (JPEOCBD) | 0.5 | TRAVEL (Classroom) | 0.5
1430 | Communications-Electronics Research, Development and Engineering Center (CERDEC) Tour 6002 and Labs | 2 | Joint Program Executive Office for Chemical & Biological Defenses (JPEOCBD) | 2 | Wrap up at starting point: Review purpose, tour highlights, honorable mentions (CHRA, MEDCOM, etc.) and fill out surveys | 2.5
1500 |  |  |  |  |  | 
1530 |  |  |  |  |  | 
1600 |  |  |  |  |  | 
1630 | TRAVEL | 0.5 | TRAVEL (APG North) | 0.5 |  | 
Total Time |  | 9 |  | 9 |  | 9
Total Tour Time | 14
Total Classroom Time | 4.5
Total Travel Time | 5.5
Total Lunch Time | 3
Total AMMO | 27